## Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action | Notes
List the positives from the sprint - what processes, practices, or outcomes worked well and should be continued. | Identify challenges, blockers, or failures encountered during the sprint that need to be addressed. | Brainstorm improvements, new approaches, or experiments the team would like to try going forward. | Define concrete, actionable steps the team will take based on what went well and poorly. | Any additional context, sprint number, dates, or reference information.
Core ML pipeline implemented successfully. MultimodalViT model architecture designed and trained with 93% accuracy. Database schema and FastAPI skeleton set up quickly. Docker PostgreSQL container worked out of the box. Basic dashboard with field grid visualisation was well-received by the team. | Generating the synthetic multimodal dataset took longer than expected. Initial model accuracy was only 71% before incorporating weather data. Setting up the async SQLAlchemy database layer had compatibility issues with FastAPI lifespan events. | Incorporate live weather data into inference to improve model generalisation. Add a second image-only ViT model for specific disease identification. Plan for a sensor simulator to test without real IoT hardware. | Integrate OpenWeatherMap API into the inference pipeline before Sprint 2. Source a pretrained ViT model from HuggingFace for the disease classifier. Begin designing the IoT simulator alongside Sprint 2 feature work. | Sprint 1 - January 2026
All 6 dashboard pages (Dashboard, Crop Analysis, Disease Analysis, Drone Management, Water Supply, Calibration) delivered. Disease classifier achieved near-100% confidence on test images. IoT sensor simulator and drone flight simulator provided excellent test coverage. Alert engine (both model-based and threshold-based) worked reliably. | CORS issues between React frontend and FastAPI backend caused integration delays in week 1. Frontend state management for real-time alert updates was tricky. Water supply page required multiple UI iterations to feel intuitive. | Add an AI chatbot to allow natural language control of farm operations. Implement irrigation scheduling to reduce manual intervention. Use the drone simulator to automate regression testing. | Spike AgriBot in Sprint 3 using Groq API with function/tool calling. Design irrigation schedule data model and cron executor. Add drone_test.py --sweep to CI pipeline for automated regression. | Sprint 2 - February 2026
AgriBot with Groq Llama 3.3 70B and tool calling worked first attempt. Voice I/O (Web Speech API) integrated cleanly into the chat page with STT and TTS. Irrigation scheduling with APScheduler worked reliably. Full Docker Compose stack (all 3 services) deployed successfully. README updated to document all new features. | Groq API rate limiting (free tier) caused intermittent delays during chatbot testing. Web Speech API is not supported in all browsers (Firefox desktop). Initial tool definitions for AgriBot were too broad, causing occasional hallucinated tool calls. | Add response caching for common AgriBot queries. Implement a WebSocket-based real-time dashboard for live sensor updates. Add per-role access control (Admin / Farm Manager / Field Operator / Viewer). | Evaluate Groq paid tier or implement local LLM fallback for production. Add browser compatibility warning for voice features. Refine tool schemas with stricter parameter validation to reduce hallucinations. | Sprint 3 - March 2026